## Sheet1
Defect Tracking and Update
S.no | Testing Date | Checklist Entry date | Test Id no | Test name | List of findings bugs during the test | Status/Fixed by dev/Not yet | Comment
1 | 19-01-2023 | 25-01-2023 | SAS_02 | Super Admin Login page | The login page screen has not responsive when resizing it. | Not yet completed
2 |  |  | SAS_04 |  | In login page,By default, The cursor has not remained on the login id text box | Not yet completed
3 |  |  | SAS_09 |  | The validation message not showing, when the user leaves the both login id and password field | Not yet completed
4 |  |  | SAS_11 |  | In Login user Enter -->Invalid Email and valid password It doesn't navigate to home page. But,the error message not showing, when user enter the incorrect Id | Not yet completed
5 |  |  | SAS_12 |  | In Login user Enter -> Valid Email and Invalid Password It doesn't navigate to home page. But,the error message not showing, when user enter the incorrect password | Not yet completed
6 |  |  | SAS_13 |  | In Login page user Enter -> Both Invalid Email and password It doesn't navigate to home page. But,the error message not showing, when user enter the incorrect credentials | Not yet completed
7 |  |  | SAS_14 |  | In Login page user Click -> Forget password The forget password link not working | Not yet completed
S.no | Testing Date | Checklist Entry date | Test Id no | Test name | List of findings bugs during the test | Status/completed by dev/Not yet | Comment
8 | 19-01-2023 | 25-01-2023 | SAO_02 | Super Admin Organization | The mentioned UI fields are displayed properly, Except "Logo" In home page, logo image is missing. There is text instead of logo image. | Not yet completed
9 |  |  | SAO_03 |  | The screen has not responsive when resizing it. When resizing the screen, the profile icon text, oraganization status,edit and delete buttons alignments are changing | Not yet completed
10 |  |  | SAO_05 |  | In Add organization page The given UI fields have been displayed properly, except "CANCEL & SAVE" buttons The "CANCEL& SAVE buttons are merged | Not yet completed
11 |  |  | SAO_08 |  | In Add organization page Verify if the user cannot proceed without filling all the mandatory fields. "Error message not showing" | Not yet completed
12 |  |  | SAO_12 |  | In Add organization page To verify -> First name & Last name Check if the speical character adding in first and lastname, it will throw an error message, or not "Error message not showing" | Not yet completed
13 |  |  | SAO_14 |  | In Add organization page To verify -> Email Check if the user enter the invalid email, the validation message will show or not" "Error message not showing" | Not yet completed
14 |  |  | SAO_16 |  | In Add organization page To verify -> Contact number Check if the user enter the Invalid number, the validation message will show or not "Error message not showing" | Not yet completed
15 |  |  | SAO_18 |  | In Add organization page To verify -> District Check if the user enter the district name ,Automatic suggestion will show on the field" "The automatic suggestion not showing" | Not yet completed
16 |  |  | SAO_19 |  | In Add organization page To verify -> State Check if the user enter the district name ,the 'Automatic' suggestion will show on the field "The automatic suggestion not showing" | Not yet completed
17 |  |  | SAO_20 |  | In Add organization To verify -> Country Check if the user enter the district name ,the 'Automatic' suggestion will show on the field "The automatic suggestion not showing" | Not yet completed
18 |  |  | SAO_24 |  | In Add organization page "To verify -> Save button Check whether the confirmation message showing or not when the user enters valid data in all field and click on the save button" "Message not showing" | Not yet completed
19 |  |  | SAO_25 |  | In Add organization page To verify -> Save button Check whether the alert message for the mandatory field showing or not when the user clicks on save button without entering data in the mandatory field. | Not yet
20 |  |  | SAO_25 |  | In Add organization page To verify -> Save button Check whether the alert message for the mandatory field showing or not when the user clicks on save button without entering data in the mandatory field. | Not yet completed
21 |  |  | SAO_26 |  | In Add organization page Click -> Save Check whether the user completed the madatory fields, after clicks the save button, the current page will disappear automatically or not "The page has not disappeared" | Not yet completed
22 |  |  | SAO_30 |  | In organization list page "To verify -> Edit Check if the user clicks the edit button, the edit page will open or not" "Edit Page has opened. But,there is no fields | Not yet completed
23 |  |  | SAO_31 |  | In oragnization list page "To verify -> Row delete Check if the user clicks the delete button, selected organization will delete or not" "Pop-up opened. But, there is no Yes or No button" | Not yet completed
24 |  |  | SAO_32 |  | In organization list page To verify -> Search bar Verify suggestions shown or not on adding a keyword to search. "Search bar not working" | Not yet completed