## Sheet1
Ticket no | Test description | Issue Type | Status | Comment | Attachment
REVOPS-8 | Testing - Write test cases for Authentication screens | Main Issue | Move to testing | Final testcase reviewed by priya
REVOPS-30 | Multi factor authentication check | Child Issue for (Revops-8) | To Do | Waiting for wire frame from bhavani mam
REVOPS-13 | Testing - Test cases for admin Console main page | Main Issue | In progress | Draft test case has attached . Waiting for updated wireframes
REVOPS-14 | Testing - Test cases for Teams and billing page | Main Issue | In progress | Draft test case has attached . Waiting for updated wireframes
REVOPS-24 | Team - Teams details display & access management | Child Issue for (Revops-14) | To Do | Waiting for wire frame from bhavani mam
REVOPS-25 | Billing - Plan options | Child Issue for (Revops-14) | To Do | Waiting for wire frame from bhavani mam
REVOPS-26 | Billing - Account Owner display | Child Issue for (Revops-14) | To Do | Waiting for wire frame from bhavani mam
REVOPS-27 | Billing - Invoice History | Child Issue for (Revops-14) | To Do | Waiting for wire frame from bhavani mam
REVOPS-28 | Billing - plan check out | Child Issue for (Revops-14) | To Do | Waiting for wire frame from bhavani mam
REVOPS-29 | Billing - Payment gateway | Child Issue for (Revops-14) | To Do | Waiting for wire frame from bhavani mam